## Sheet1
TO COMPULETE
Sr.No | API Name | Status | Days | Hour | IMP
1 | college creation api | done
2 | delte college api | done
3 | admin login api | done
4 | time table creation api | not done |  | 5 hour | yes
5 | time table view api | not done |  | 1 hour | yes
6 | time table edit api | not done |  | 3 hour
7 | time table delete api | not done |  | 1 hour
8 | fetch all department subject list api | not done |  | 2 hour | yes
9 | student single creation api | not done |  | 5 hour | yes
10 | H.O.D Subject assign (self ) api | not done |  | 2 hour | yes
11 | H.O.D Subject assign ( A.P. ) api | not done
11 | Assigned subject view (H.O.D ) api | not done |  | 1 hour | yes
12 | delete assigned subject api | not done |  | 1 hour
13 | Specific faculty lectures view api | not done |  | 5 hour | yes
14 | Faculty attendance taking api | not done |  | 8 hour | yes
15 | Student time table view api | not done |  | 2 hour | yes
16 | Student add faces api | not done |  | 3 hour | yes
17 | Student current day attendane api | not done |  | 2 hour | yes
18 | Student overall attendnace api | not done |  | 3 hour
19 | College management creation api | not done |  | 2 hour
20 | College management deletioin api | not done |  | 1 hour
21 | H.O.D creation by management api | not done |  | 2 hour
22 | H.O.D deletion by management api | not done |  | 1 hour
23 | H.O.D edit details by management api | not done |  | 2 hour
24 | Assistance profeessor creation api | not done |  | 2 hour
55 hour